## sprint
lamba yansın
lamba değişik renklerde yansın
the box should talk	sonra
hareket sensörüyle lambalar çalışsın
kutunun interneti çalışsın
sunucu hava tahminlerini alsın
renkler nasıl olacak?
yağış olacaksa yanıp sönsün
rüzgarı da göstersin
internet settings of the box	yakında
software updates	sonra
design for 10s of boxes	yakında
design for 1000s of boxes	sonra
measuring the battery values	yakında
cihaz pille çalışsın	sonra
farklı lambalar yanıp sönsün
lambalar farklı saatleri göstersin
lambalar sıcaklık göstersin
lambalar yağış göstersin
lambalar havanın açık/bulutlu olduğunu göstersin
lambalar farklı günleri göstersin
prototip taslak kutu
mirror prototype design	yakında
creative designs	yakında
umbrella cries	sonra
single lamp version	sonra
mobile widget	sonra
box setup and reset	sonra
city code
market analysis
kosgeb desteği alacak mıyız?
make users use the prototype
lorawan usage	sonra
hedef kitle
cihaz 12V adaptörle çalışsın
hareket sensörüyle enerji tasarrufu	yakında
the lamps should work with sensor
revisions of the application kosgeb
the device should work with 5V adaptor
it should work w a USB connector
it should work w a micro USB connector	sonra
registration page for the user	prepare a web page
prepare a user's manuel	write the document
finetune the colors	discussion
smaller box	find and get the box
smaller sensor
Box-server communication
entering different cities	yakında
sıcaklık, nem, CO2, duman ölçümü	sonra
e book version	sonra
tablet version	sonra
watch version	sonra
stamp design	sonra
revising the manual	setup	registration	colored	turkish	sticked to the back of the box	proofread
revising the screen design	white glass	plexiglass
finetune the colors again
as a user, I would like to see the demo mode	soon
brand name	soon
how to use video	later
do not show weird stuff when plugged in
keep some boxes ready to give	later
different box designs	material	color
research about manufacturing
revisions of the application kosgeb
research about legal issues	later
work for different climates	later
as a user, I would like to enter a place which is far from the city center	mid
as a designer, I need correct weather forecast from the website	soon
as a user, I don't want the box on all the time	soon
as a user, I want the box work smoothly so that I don't have to plug it on and off constantly	soon
as a user, I want to know when I can use my mobile to connect to the device	soon
as a user, I want a mobile app where I can manage wifi and city settings	later
as a user, I want a product URL on the box	soon
as a developer, I would want the box have an API	later
as a user, I would like to change the colors	later
as a user, I want to change the temperature ranges	later
as a developer, I want to add the manual to the website and vice versa	soon
as a user, I would like to see somewhere else's weather, too	soon
as a user, I would like a smooth unboxing process	soon
as a user, I would like to give the box to someone else	soon
as a user, I want to know what to do when my internet is broken	soon
as a developer, I need to know when and why the device is stuck	soon
as a developer, I would like to log weather forecast and leds for debugging purposes	soon
as a user, I would like to choose any city in the world	later
as a user, I would like to see a copy of the leds on the web	soon

## 1. hafta
lamba yansın	esp ye kod yüklemek	esp bulmak	breadboard	programlama kablosu bulmak	kod yazmak
kutunun interneti çalışsın	wifi programı yazmak
yağış olacaksa yanıp sönsün	internete bağlanmak	komut alma kodu yazmak	yağış web sayfası yapmak

## 2. hafta
Blocker: 3lü lamba derdine çözüm
lamba değişik renklerde yansın	striplerdeki lambaları / Kontrol etmek	sunucu renkleri / Versin	cihaz renkleri / Alsın
renkler nasıl olacak?	doküman yazmak	sunucu dokümana göre / Hava durumundan renkleri / Üretsin
farklı lambalar yanıp sönsün	yanıp sönmesi kontrolü
lambalar farklı saatleri göstersin	hangi saatleri göstersin
lambalar sıcaklık göstersin
lambalar yağış göstersin
lambalar havanın açık/bulutlu olduğunu / Göstersin
lambalar farklı günleri göstersin	hangi günleri göstersin
prototip taslak kutu	kutuya ledler yapışacak	kutu bulmak	breadboard koymak
pazar analizi	benzer ürünleri araştırmak	mobil hava durumu appleri	insanlar hava durumu bilgisini nerden alıyor?
hedef kitle	3-4 kişi için	geniş kapsamda kimler?
cihaz 12V adaptörle çalışsın	çevirici bulmak	adaptörü çeviriciye bağlamak
butona basınca lambalar çalışsın	buton bulmak	hareket sensörünü incelemek

## 3rd week
the lamps should light in different colors	writing a code for colors
the lamps should work with the sensor	write seperate code
how about the colors?	write a document
different lamps should go on and off	write a code
the lamps should show different hrs	design a json format	parse the json	generate the json
temperature	decide the colors	parse the open weather API
different days	study 2day and 5 day forecasts	generate json
market analysis	how people get weather info	what other things the box could show	pricing
target group	people who would be interested
the device should work with 5V adaptor	find a 5v adaptor	cut a usb cable

## 4th week
prototype box design	come up w a design
market analysis	internet research	pricing
make users use the prototype	find the users	4 users	ordering the equipment
target group	research
revisions of the application kosgeb	documentation
registration page for the user	prepare a web page	city code	name, contact info	include our contact info
prepare a user's manuel	write the document
finetune the colors	discussion	revision	creating virtual cities
smaller box	find and get the box	put the equipment into the box
smaller sensor	get the sensors	try them
Box-server communication	the box should send info to the server when it is used

## 5th week
				DONE
internet settings of the box	wifi login page	leds for setup mode	leds for searching	leds for getting the data	login page automatically opened, different lights for different modes
measuring the battery values	find a device to report current	record the current values with different settings	reporting the times that the sensor is working	buy the device	avg power in different modes, avg daily power for each user
creative designs	picture	mirror	5 designs		1 pager, image+how it works	mesut, giray
make users use the prototype	Finding 4 profiles
entering different cities
revising the manual	setup	registration	colored	turkish	sticked to the back of the box	proofread
revising the screen design	white glass	plexiglass
finetune the colors again
do not show weird stuff when / Plugged in
different box designs	material	color
research about manufacturing for 10s
revisions of the application kosgeb

## 6th week
STORIES	Task 1	Task 2	Task 3	Task 4	DONE
internet settings of the box	wifi login page	leds for setup mode	leds for searching	leds for getting the data	login page automatically opened, different lights for different modes, chech from iphone and android
make users use the prototype	Finding 4 profiles: giray, eren, mustafa, rober	go and take 3 esp's from kadıkoy	Create 2 more boxes	hand the boxes to users	getting feedback from 4 users
finetune the colors again	clouds dim	snow	thunderstorm flashing white		clouds, snow, thunderstorm, temp. range
as a user, I don't want the box on all the time	finetune the sensitivity				the screen goes blank for 30 mins
as a user, I want the box work smoothly so that I don't have to plug it on and off constantly	temporary log	send the log to the server			the box is not stuck for 2 days
as a user, I want a product URL on the box	added to the manual	written on the paper sticked to the box
as a developer, I want to add the manual to the website and vice versa	write the web address to the manual	write the manual to the website
as a user, I would like to see somewhere else's weather, too	investigate the API	change the interface to type the city name	choose the city names from the map		when the user picks a different city, he/she can see the weather there
as a user, I would like a smooth unboxing process	setup in the manual	design leds for configuration	set the default city from the order		get mesut unbox the device
as a developer, I would like to log weather forecast and leds for debugging purposes	log the API and led values by date and time	on the debug page, the developper can pick a specific device and a past time and date			make the box show yesterday's weather